## Slide 1: Red Bank Commission Goal Update: Develop a master plan for Red Bank Commissioner Pete Phillips City Manager Martin Granum
20 Sept 2022

## Slide 2: Strategic Planning: Three Applications
Commission Priorities
Staff/Department Priorities (Municipal Service Delivery Priorities)
Comprehensive Planning
Notes: Strategic Planning: as a by-product of our recent FRBMSS discussion at the 1 Feb Commission Meeting you identified a need to have a conversation about ‘strategic planning’… what it is, what we need, how we might go about it… I am working with our staff, SETD and MTAS and will guide us thru a conversation at our next work session on the 15th. Here’s a peak under the tent… in my view, there are three levels of what we might call ‘strategic planning’:

## Slide 3: Reminder… from the Commission Retreat (4 Apr ‘22 MTAS Report)
Mission (should explain the purpose of a city’s being and why it exists): The City of Red Bank is a safe and thriving small-town community with an engaging, transparent government that builds on our rich history, provides excellent and efficient services, and welcomes all who live, work, worship, and play.
Vision (builds upon the city’s mission and takes it to the next level; a desired future state): Red Bank will lead our vibrant and proud community with a commitment to excellence, safety, and enhancing our neighborhood character for future generations.

## Slide 4: Reminder… from the Commission Retreat (4 Apr ‘22 MTAS Report)
Goals (after an environmental analysis and applying the SWOT methodology, issues were identified and ultimately goals were set that: address the key issues, meet the mission of the City and help the City to achieve its vision):
  Create adequate digital capacity (Mayor Berry; Chief Seymour)
  Revamp stormwater ordinance and operations and stormwater fee structure (Vice Mayor Dalton; Director Alexander)
  Develop a master plan for Red Bank (Commissioner Phillips; City Manager Granum)
  Develop parks within ten-minute walk initiative (Commissioner LeCompte; Director Tate)
  Beautification of city – throughout with an emphasis on Dayton Blvd (Commissioner Jeno; Chief Sylar)

## Slide 5: Develop a master plan for Red Bank Steering Committee Members:
Commissioner Pete Phillips
Commissioner Becky Browder, Planning Commission Chair
Ashley Yingling Gates, Planner with SETD
Public Works Representatives:
  Director
  Codes Enforcement Officer
  Community Development/Planner
City Manager Martin Granum

## Slide 6: Big Picture Overview
Draft “Roadmap to a Master Plan Comprehensive Plan”
  Preview the roadmap tonight
  Discuss with Steering Group
  Finalize the Roadmap (staff)
Complete the recruitment ongoing for the Community Development/Planner FTE
Follow the roadmap… “execute”

## Slide 7: Roadmap
Objective: To create a Comprehensive Plan that reflects the community’s vision for Red Bank, while taking into account current conditions and future needs of all Red Bank’s businesses and residents. The plan will include:
Comprehensive transportation plan, including identification of the needed vehicular, transit, bike, and pedestrian infrastructure
Comprehensive land use plan, including land use map, plan for future development, and recommended updates to the Zoning Ordinance and Subdivision Regulations
Needs assessment for recreational facilities and programs
Plan to meet the requirements of the Nation Park Service conversion agreement
Small area plan for the former Red Bank Middle School Site

## Slide 8: Roadmap… 6 Steps
Ongoing: Work with TDOT and TDOT consultant to complete the Urban Mobility Study under the Urban Transportation Planning Grant
  Steering Committee to be Appointed in September
  Transportation Plan scheduled to be completed June 2023
Develop Comprehensive Plan Bid Documents
  Working with Southeast Tennessee Development District, a Request for Qualifications will be developed to hire a consultant that can deliver all aspects of the Comprehensive Plan other than the portion that is covered by the Urban Transportation Planning Grant
  By November 2022

## Slide 9: Roadmap… 6 Steps (continued)
Prepare Data and Contacts for Consultant
  Website to be created by SETD
  GIS Data to be provided by Hamilton County and SETD
  Additional data will be gathered through the Transportation Plan
  SETD can provide demographic and market data
  Leadership and community members to identify key stakeholders that should be engaged during the planning process, and begin contacting them
  November 2022 – January 2023
Select Consultant
  Steering Committee will review and recommend consultant
  December 2022 – January 2023

## Slide 10: Roadmap… 6 Steps (continued)
Comprehensive Plan Execution
  The selected consultant will lead the planning process for the following components:
    Land use plan
    Recreation needs assessment and plan
    Additional transportation planning, if needed
    Recommended ordinance and policy updates
  Steps in the planning process will include:
    Analysis of data including: market data, demographic data, current development patterns, land topography
    Community outreach and visioning process
    Assessment of community assets and needs
    Drafting of Plan
    Community feedback and plan revisions
  Timeline: 9-month process (“Three Seasons”)

## Slide 11: Roadmap… 6 Steps (continued)
Small Area Plan Execution
  Consultant to focus on the Former Red Bank Middle School site in the context of the Comprehensive Plan. This process will involve:
    Site assessments, if needed
    Market research, including both quantitative and qualitative
    Community input sessions
  The consultant will provide:
    Report on the community input received
    Recommendation, which may provide the Board of Commissioners with multiple options, for the use of this land
    Recommended next steps
  Timeline: 3 to 6 months (Nov 23 to Jan/Apr 24)

## Slide 12: Develop a master plan for Red Bank Commissioner Pete Phillips City Manager Martin Granum Discussion
20 Sept 2022

## Slide 13: Next Goal Update…
Create adequate digital capacity
  Mayor Berry
  Chief Seymour
4 Oct 2022 Work Session